## Versions released and goals
Last Update: 10/5/2023 | v0 | v1 | v1.1 | v1.2 | v1.3 - IN REVIEW | v1.4 - FY24 CLEAN VERSION | Short term goals 1 | Short term goals 2 | Long term goals
Official Merge Date | 2022-11-21 | 2023-07-31
Summary | Prototype | Useable pipeline for local matches (combined with legacy preprocessing) | Added zip/county information for non-local matches, flexible acceptance criteria (to run full DCFS undup and secondary match for Family Networks project) | Complete pipeline for generating match crosswalk (using v1.1 logic) | Fixed performance issue with large datasets |  | Make the current version smooth | Go deeper into some of the "for later" problems | Dreams
Update - match logic | Designed and implemented prototype match logic, including blocking strategies, similarity metrics, acceptance criteria | Improved match logic accuracy | Added zip/county into match logic |  |  |  | Replace soundex with double-metaphone | Refine weight calculation based on review of match analysis and samples from prototype tests | Add more complex name comparison algorithms (e.g. arrays, tweaks based on results from equity checks); Add geodata as blocking and more complex comparison variables (pending ch_address_id unduplication)
Update - functional/structural | Designed and implemented postprocessing algorithm that creates match crosswalk | Streamlined and modularized pipeline to reduce dependencies and remove obsolete code; Created configuration module and central control script to allow for better documentation and fast rerun; Generates and logs key match metrics (e.g. # IDs matched) automatically; Created script to join crosswalk to original data; | Created option to use user-defined acceptance criteria instead of default for each pass for project-specific matches (define in config.py) | Added preprocessing template - created middle name aliases when people have multiple middle names Cleaned up various modules and standardized output names | Fixed performance issue with large datasets: matching no longer holds all data in memory; drops blocking tables once used Move sorting from postprocessing to matching; Functions for printing out record pairs for easy clerical review; | Clean up pipeline Update workflow to have a csv path and a postgres path | AL - Round out workflow from raw data to end-product (including data storage, match vs project directory, server use, etc); [v1.4] AL - Clean up pipeline with new preprocessing component; [v1.4] SS - Handle matches with multiple IDs, potentially with different strengths (i.e. CHA undup); [in progress as part of the collaborative project] Working session - Draft and pilot match analysis to include in linkage memo; | Pilot sampling and reviewing functions to test what is desirable and how it could fit into the workflow; Pilot intersectional equity checks, the results of which informs directions to expand on name matching; | Integrate automated intersectional equity check into post-match reporting; Integrate automated full match analysis in linkage memo; Find sustainable ways to block on large data (DCFS) - maybe breaking blocking passes;
Update - documentation/other | N/A | Created full README | N/A |  |  |  | W/ Emily - Draft user manual; W/ Emily - Create tool name; W/ Emily - Collaborate on when/how sensitivity testing can happen (*Family Networks application) |  | Create working version of user manual
Official links produced | N/A | SY21-22 YDC except for CHA undup (CPS undup, YG-CPS, ASM-CPS, CHA-CPS, DFSS-CPS, BUILD-CPS) | SY22-23 Oak Park (preprocessing was separate) Family Networks first-round dedup (subset of DCFS data) | SY22-23 CPS undup SY22-23 YDC except for CHA undup match portion (CPS undup, ASM-CPS, preproc and postproc of CHA undup, CHA-CPS, [Tentative] DFSS-CPS, [Tentative] YG-CPS, [Tentative] BUILD-CPS) Family Networks second-round dedup within household | [Tentative] DCFS undup 2021 DCFS undup 2023?
Tests run | SY20-21 YG-CPS, DCFS undup 2019 (Cook county only) | SY20-21 YDC except for CHA undup, DCFS undup 2019 (Cook county only) | DCFS undup 2019 | SY21-22 CPS, YG, ASM, CHA, BUILD | DCFS undup 2021 |  | Test match results between other admin datasets (e.g. CHILD-CCALD, other active links) and compare with BigMatch results
Link to logic | n/a | https://chapinhall.sharepoint.com/:w:/r/sites/ETL/Shared%20Documents/Record%20linkage/Design/Record%20Linkage%20Tool%20Design%20(v1).docx?d=w21eeeadf8c274e96abd6dd02e716cc62&csf=1&web=1&e=ZUVgZy | https://chapinhall.sharepoint.com/:w:/r/sites/ETL/Shared%20Documents/Record%20linkage/Design/Record%20Linkage%20v1.1%20Match%20Logic.docx?d=w547305039b2041518f0ccf48b2af8a42&csf=1&web=1&e=msDBET | Same as v1.1 | Same as v1.1
Link to commit | https://chudev01.chapinhall.org/record-linkage/record-linkage-v0/-/commit/0a7afb01842583e6b763db8fdd8ae0a9f9075b4d | https://chudev01.chapinhall.org/record-linkage/record-linkage-v0/-/commit/a2f4551b52914b4b2acf9159f2ee17a7cca53d88 | tbd | tbd | tbd
Key constraints | Logic not ready to use for production | Only applies to matches in the same county; Imports legacy preprocessed files in fwf format, and the tool begins applicable there; | Imports legacy preprocessed files in fwf format, and the tool begins applicable there; Can't compare multiple common IDs; Can't add additional blocking passes, because relationship between pass number and acceptance criteria is hard coded; | Can't compare multiple common IDs; Can't add additional blocking passes, because relationship between pass number and acceptance criteria is hard coded;
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I need to think on this and double-check some things, but I think with the new way I set up the acceptance criteria we might be able to add multiple common ids or additional blocks, since the pass number and acceptance criteria are no longer hard coded.